## Issues
Don't overwrite this column. Paste new data from B onwards
Linked Epic Name | Issue key | Issue id | Issue Type | Summary | Status | Custom field (Epic Link) | Custom field (Epic Name) | Custom field (Epic Status) | Fix Version/s | Resolution | Resolved | Priority | Created | Updated | Due Date
| PHOT-28 | 10907 | Story | Improve sign up screen | To Do | [6 empty] | Medium | 2018-02-12 20:40 | 2018-02-12 20:40
| PHOT-27 | 10906 | Task | Rewrite backup scripts | To Do | [6 empty] | Medium | 2018-02-12 20:40 | 2018-02-12 20:40
| PHOT-26 | 10905 | Task | Upgrade Postgres | To Do | [6 empty] | Medium | 2018-02-12 20:39 | 2018-02-12 20:39
Gallery view (web) | PHOT-24 | 10827 | Story | Responsive photo gallery view | To Do | PHOT-3 | [5 empty] | Medium | 2018-01-29 22:22 | 2018-02-12 19:33
Gallery view (web) | PHOT-23 | 10826 | Story | List / Gallery view toggle | To Do | PHOT-3 | [5 empty] | Medium | 2018-01-29 22:22 | 2018-02-12 19:33
Gallery view (web) | PHOT-22 | 10825 | Bug | Infinite scroll not loading after second data screen | In Progress | PHOT-3 | [5 empty] | Medium | 2018-01-29 22:21 | 2018-02-12 19:33
Gallery view (web) | PHOT-21 | 10824 | Task | Research how to optimize page load | To Do | PHOT-3 | [5 empty] | Medium | 2018-01-29 22:21 | 2018-02-12 19:33
Notification actions | PHOT-20 | 10823 | Story | View related pictures | Released | PHOT-17 |  |  | Version 1.9 | Done | 2018-01-29 20:50 | Medium | 2018-01-29 18:37 | 2018-02-12 19:33
Notification actions | PHOT-19 | 10822 | Story | View new likes | Released | PHOT-17 |  |  | Version 1.9 | Done | 2018-01-29 20:50 | Medium | 2018-01-29 18:37 | 2018-02-12 19:33
Notification actions | PHOT-18 | 10821 | Story | Reply to comment | Released | PHOT-17 |  |  | Version 1.9 | Done | 2018-01-29 20:49 | Medium | 2018-01-29 18:36 | 2018-02-12 19:33
| PHOT-17 | 10820 | Epic | Notification actions | Released |  | Notification actions | To Do |  |  |  | Medium | 2018-01-29 18:35 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-16 | 10819 | Story | Billing failed message | To Do | PHOT-2 |  |  | Version 2.1 |  |  | Medium | 2017-12-15 18:08 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-15 | 10818 | Story | Billing succeeded message | To Do | PHOT-2 |  |  | Version 2.1 |  |  | Medium | 2017-12-15 18:07 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-14 | 10817 | Story | Pro upgrade message | To Do | PHOT-2 |  |  | Version 2.1 |  |  | Medium | 2017-12-15 18:06 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-13 | 10816 | Story | Tips and tricks message | To Do | PHOT-2 |  |  | Version 2.1 |  |  | Medium | 2017-12-15 18:05 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-12 | 10815 | Story | Warm user message | To Do | PHOT-2 |  |  | Version 2.1 |  |  | Medium | 2017-12-15 16:24 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-11 | 10814 | Story | Onboarding stuck user message | To Do | PHOT-2 |  |  | Version 2.0 |  |  | Medium | 2017-12-15 16:24 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-10 | 10813 | Story | New user welcome message | In Progress | PHOT-2 |  |  | Version 2.0 |  |  | Medium | 2017-12-15 16:24 | 2018-02-12 19:33
Lifecycle emails and notifications | PHOT-9 | 10812 | Story | User notification preferences (in-app or email) for all notification types | To Do | PHOT-2 |  |  | Version 2.0 |  |  | Medium | 2017-12-15 16:23 | 2018-02-12 19:33
Nested comments | PHOT-8 | 10811 | Story | Expand/collapse toggle button | To Do | PHOT-1 |  |  | Version 2.0 |  |  | Medium | 2017-12-14 10:13 | 2018-02-12 19:33
Nested comments | PHOT-7 | 10810 | Story | Nested comment thread view | In Progress | PHOT-1 |  |  | Version 2.0 |  |  | Medium | 2017-12-14 10:12 | 2018-02-12 19:33
Nested comments | PHOT-6 | 10809 | Task | Add indentation level to comments in DB | Released | PHOT-1 |  |  | Version 2.0 | Done | 2018-01-29 21:55 | Medium | 2017-12-14 10:05 | 2018-02-12 19:33
Nested comments | PHOT-5 | 10808 | Story | Nested reply button | Done | PHOT-1 |  |  | Version 2.0 |  |  | Medium | 2017-12-14 10:03 | 2018-02-12 19:33
| PHOT-4 | 10807 | Epic | Multiple smaller UX improvements | To Do |  | UX improvements | To Do |  |  |  | Medium | 2017-12-14 09:46 | 2018-02-12 19:33
| PHOT-3 | 10806 | Epic | Gallery view (web) | In Progress |  | Gallery view (web) | To Do |  |  |  | Medium | 2017-12-14 09:44 | 2018-02-12 19:33
| PHOT-2 | 10805 | Epic | Lifecycle emails and notifications | In Progress |  | Lifecycle emails and notifications | To Do |  |  |  | Medium | 2017-12-14 09:44 | 2018-02-12 19:33
| PHOT-1 | 10804 | Epic | Nested comments | In Progress |  | Nested comments | To Do |  |  |  | Medium | 2017-12-14 09:39 | 2018-02-12 19:33

## Progress - Epics
Progress by status | Column Labels
Row Labels | Done | In Progress | Released | To Do | Grand Total
Gallery view (web) | 0% | 25% | 0% | 75% | 100%
Infinite scroll not loading after second data screen | 0% | 100% | 0% | 0% | 100%
List / Gallery view toggle | 0% | 0% | 0% | 100% | 100%
Research how to optimize page load | 0% | 0% | 0% | 100% | 100%
Responsive photo gallery view | 0% | 0% | 0% | 100% | 100%
Lifecycle emails and notifications | 0% | 12.5% | 0% | 87.5% | 100%
Billing failed message | 0% | 0% | 0% | 100% | 100%
Billing succeeded message | 0% | 0% | 0% | 100% | 100%
New user welcome message | 0% | 100% | 0% | 0% | 100%
Onboarding stuck user message | 0% | 0% | 0% | 100% | 100%
Pro upgrade message | 0% | 0% | 0% | 100% | 100%
Tips and tricks message | 0% | 0% | 0% | 100% | 100%
User notification preferences (in-app or email) for all notification types | 0% | 0% | 0% | 100% | 100%
Warm user message | 0% | 0% | 0% | 100% | 100%
Nested comments | 25% | 25% | 25% | 25% | 100%
Add indentation level to comments in DB | 0% | 0% | 100% | 0% | 100%
Expand/collapse toggle button | 0% | 0% | 0% | 100% | 100%
Nested comment thread view | 0% | 100% | 0% | 0% | 100%
Nested reply button | 100% | 0% | 0% | 0% | 100%
Notification actions | 0% | 0% | 100% | 0% | 100%
Grand Total | 5.263% | 15.79% | 21.05% | 57.89% | 100%

## Progress - By Type
Count of Status | Column Labels
Row Labels | In Progress | Grand Total
Bug | 1 | 1
Infinite scroll not loading after second data screen | 1 | 1
Story | 2 | 2
Nested comment thread view | 1 | 1
New user welcome message | 1 | 1
Grand Total | 3 | 3

## Recently completed
Resolved | (All)
Count of Status | Column Labels
Row Labels | Done | Released | Grand Total
Story | 1 | 3 | 4
Nested reply button | 1 |  | 1
Reply to comment |  | 1 | 1
View new likes |  | 1 | 1
View related pictures |  | 1 | 1
Task |  | 1 | 1
Add indentation level to comments in DB |  | 1 | 1
Grand Total | 1 | 4 | 5

## Releases
Count of Status2 | Column Labels
Row Labels | Done | In Progress | Released | To Do | Grand Total
Version 1.9 | 0% | 0% | 100% | 0% | 100%
Story | 0% | 0% | 100% | 0% | 100%
Reply to comment | 0% | 0% | 100% | 0% | 100%
View new likes | 0% | 0% | 100% | 0% | 100%
View related pictures | 0% | 0% | 100% | 0% | 100%
Version 2.0 | 14.29% | 28.57% | 14.29% | 42.86% | 100%
Story | 16.67% | 33.33% | 0% | 50% | 100%
Expand/collapse toggle button | 0% | 0% | 0% | 100% | 100%
Nested comment thread view | 0% | 100% | 0% | 0% | 100%
Nested reply button | 100% | 0% | 0% | 0% | 100%
New user welcome message | 0% | 100% | 0% | 0% | 100%
Onboarding stuck user message | 0% | 0% | 0% | 100% | 100%
User notification preferences (in-app or email) for all notification types | 0% | 0% | 0% | 100% | 100%
Task | 0% | 0% | 100% | 0% | 100%
Add indentation level to comments in DB | 0% | 0% | 100% | 0% | 100%
Version 2.1 | 0% | 0% | 0% | 100% | 100%
(blank) | 0% | 33.33% | 8.333% | 58.33% | 100%
Grand Total | 3.704% | 22.22% | 18.52% | 55.56% | 100%